Terms of Reference

Programme Evaluation — ILMpact

Purpose

The evaluation will assess the extent to which the ILMpact remedial learning model has improved student learning outcomes and generated evidence to inform future scale-up. Specifically, the evaluation aims to: (1) independently validate the quality, reliability, and robustness of existing programme and assessment data; (2) assess the effectiveness of the model in improving learning outcomes; and (3) analyse the costs and value for money associated with achieving these results to support decisions on scalability and sustainability.

| Document owner | Rizwan Mehmood |
| --- | --- |
| Document author | Rizwan Mehmood |
| Current version | Version 1 |
| Issue date | 18 May 2026 |
| Apply By | 15 June 2026 |
| Project reference | ILMpact Programme funded by FCDO |
| File location |  |

Consultancy role title: Independent Evaluation of ILMpact Programme funded by the Foreign and Commonwealth Development Office (FCDO)

Location: Islamabad

Apply by: 15 June 2026

  - Background and context about the project

ILMpact is a multi-year education programme operating across fifteen districts in Punjab and Khyber Pakhtunkhwa with the goal of improving foundational literacy and numeracy (FLN) for marginalised children, particularly girls. The programme's primary intervention is a Remedial Learning (RL) model adapted from Teaching at the Right Level (TaRL) approaches, targeting children in Grades 3–5 enrolled in schools, and out-of-school children (OOSC) aged 8–12 through Catch-up Learning Camps (CLP) camps. The programme is also implementing other interventions as well including life skills training, STEAM club formations, accessibility, and rehabilitation in schools to differently abled children and safeguarding trainings to make schools safe and inclusive. With a whole school approach, the programme has targeted children from ECE to Grade 10 under different interventions.

In FY 2025–26, the programme reached 48,471 learners across remedial learning and 15,207 OOSC through CLP camps. Overall, the programme benefitted more than 200,000 children in 400 schools. The midline assessment results are encouraging and showed an average 14% improvement in learning outcomes across English, Urdu, and Mathematics after approximately 90 days of intervention at the midline assessment and anticipates an increase at the endline planned in April 2026. Likewise, ILMpact achieved its output level targets for all other components with first cohort of students. As the programme approaches it closure in September 2026, British Council desire an independent evaluation to assess the effectiveness and scalability of the remedial learning model and generate evidence to inform stakeholders on scale-up decisions, continuity and design challenges while implementing at scale.

  - About the role of the specialist contractor

The contractor will provide credible and actionable evidence on the performance of the ILMpact remedial learning model. Guided by the OECD-DAC evaluation criteria of Relevance, Effectiveness, Efficiency, Impact, and Sustainability, the assessment will examine the results achieved and validate the reliability and robustness of existing programme and assessment data. The contractor will assess the learning gains attributable to the programme by analysing available pre and post learning data of treatment and control groups and will also examine the robustness of data collection processes, frequency, quality and consistency of the reported data. The contractor will conduct value-for-money analysis using programme financial data and existing VfM approach adopted by the programme. The key evaluation tasks are:

- Pre-Post Comparative Analysis: To assess changes in key outcome indicators over the course of the programme, the evaluation will utilise a pre-post comparative analysis drawing upon data collected across baseline, midline, and endline rounds from both treatment and comparison groups. The dataset used for this evaluation has been gathered by a third-party monitoring firm from both control (non-implementation Tehsils) and treatment (Implementation Tehsils) from within the same districts. This approach will enable the evaluation team to examine how selected indicators have evolved over the programme period and to what extent observed changes in treatment children reflect a different trajectory as compared to children in the comparison group, thereby providing a structured basis for understanding programme contribution within the broader contextual environment. It is however acknowledged that the quality and consistency of data across collection rounds may present certain limitations, and accordingly, findings emerging from this analysis will be interpreted with due caution and presented alongside relevant caveats to ensure that conclusions remain within the bounds of what the evidence can reasonably support. The pre-post comparative analysis is therefore intended not to establish definitive causal claims but rather to offer a transparent and evidence-informed understanding of change patterns observed across the programme period, contributing meaningfully to the overall assessment of programme performance and effectiveness.

- Learning Gains (Effectiveness): Drawing on the verified dataset, assess whether the programme has produced measurable improvements in FLN outcomes across English, Urdu, and Mathematics, disaggregated by gender, province, and disability status where the data permit defined in the project LFA.

- Cost and Efficiency (proportionate VfM analysis): Develop a credible and proportionate approach to value for money for different elements of the programme, drawing on programme financials and existing VfM approach implemented by the programme. The purpose is to estimate cost per child with learning gain achieved.

- Data Quality Verification: Independently verify the quality and robustness of existing programme data, including validation of sampling approaches; consistency of data collection processes; assessment of the reliability of reported learning gains; specification of datasets used.

- Actionable Recommendations: Generate actionable recommendations for British Council, FCDO and provincial governments on model adaptation and scale-up.

  - Key Evaluation Questions

The below are proposed evaluation questions. The evaluator is expected to look deeply into the Programme’s Theory of Change, LFA, GOAL results framework and implementation plans. The evaluation questions below are organised around the major tasks outlined above. The priority is to generate independent evidence base

Relevance

- Is the TaRL-based remedial learning model relevant for Pakistani schools & context.

- Have the programme's RL and CLP interventions produced measurable improvements in FLN outcomes?

Learning Gains (Effectiveness)

- Based on the verified data, what measurable improvements in FLN outcomes (English, Urdu, Mathematics) are reported over the programme period, and how do these vary by gender, province, and disability status?

- Are the reported learning gains consistent with the programme’s baseline–endline design, and what caveats apply to their interpretation given data limitations?

Cost and Efficiency

- What is the estimated cost per learner and per unit of learning gain, drawing on available programme expenditure data?

The evaluator will provide a transparent, descriptive analysis of learning drawing on independently verified data. A proportionate VfM analysis will be undertaken drawing on programme financials and existing VfM material.

  - Methodology

The evaluation will use a mixed-methods design approach. The quantitative component will focus on independently verifying data quality and undertaking a descriptive analysis of learning gains. Through qualitative analysis, feedback, interviews and FGDs, the evaluation team will answer key evaluation questions around relevance, efficiency, sustainability and value for money.

| Method | Source / Sample | Purpose |
| --- | --- | --- |
| Data quality verification + descriptive analysis of learning gains | Programme assessment datasets (baseline and endline) provided by ILMpact. | Independently verify data quality (sampling, attrition, comparability); provide descriptive analysis of learning gains by grade, gender, and disability. Findings to be presented as indicative, not causal. |
| Key informant interviews (KIIs) | FCDO, ILMpact management, provincial education depts (CEOs/DEOs), master trainers, Lead trainers (~20-30 interviews) in KP and Punjab | Effectiveness and cost efficiency |
| Focus group discussions (FGDs) | Teachers, school management committees, parents, and learners (8–10 FGDs across both provinces) | Effectiveness and equity dimensions (learning gains by gender, disability) |
| Document review | Programme reports, MEL data, training records, learning data review, dashboard review, financial data review for Vfm analysis, After Action Review Reports and Beneficiary Surveys | Learning Impact gains, VfM analysis. Synthesis of secondary data collected by third party MEL firm |
| Report Preparation and Presentation | Presentation to British Council (ILMpact) and FCDO | Feedback incorporation |

  - Deliverables

- Inception report including finalised methodology and workplan; a data strategy notes specifying which dataset parameters (baseline–endline comparability, and how sampling, attrition, and potential sources of bias will be addressed.

- Draft evaluation report for stakeholder review.

- Final evaluation report (max forty pages, excluding annexes) covering the three evaluation tasks with findings, conclusions, and actionable recommendations. Findings on learning gains must clearly state the indicative (not causal) nature of the analysis and any caveats relating to data quality.

- Slide deck and facilitation of a validation/dissemination workshop with key stakeholders.

  - Timeline (June-July 2026)

| Days | Phase | Key Activities |
| --- | --- | --- |
| One week | Inception | Document review, methodology finalisation, data access, stakeholder mapping, inception report |
| Second-Third Week | Field data collection | KIIs and FGDs across Punjab and KP; site visits to sample schools and CLP sites |
| Fourth week | Quantitative analysis | Baseline–endline analysis; descriptive statistics; disaggregation by gender, province, and disability status |
| Fifth Week | Synthesis | Integration of findings; evidence assessment |
| Sixth Week | Validation | Validation of results before incorporating in the draft report |
| Sixth Week | Reporting | Draft report, stakeholder validation workshop, final report submission |

  - Fee

Maximum fee for the assignment will be determined based on the experience and qualification of consultant and proposed approach of evaluation.

*Note: The quotation must remain open for acceptance by the British Council for a minimum of thirty days from the date that it is issued to the British Council in response to the requirement.

  - Reporting and communication

The consultant will liaise / coordinate with the ILMpact Senior MEL Lead for assignment oversight and deliverable review.

  - Qualifications and experience required.

- Advanced degree in education, economics, social sciences, statistics, or a related field.

- Demonstrated expertise in mixed-methods evaluation; strong quantitative skills for descriptive and comparative analysis; experience with data quality assessment including sampling validation and attrition analysis.

- Strong qualitative research skills — experience facilitating FGDs and KIIs in complex, multilingual contexts.

- Prior experience evaluating education programmes in Pakistan or comparable South Asian contexts; familiarity with TaRL/FLN approaches is an advantage.

- Knowledge of evidence-based evaluation standards and OECD evaluation criteria.

- Proficiency in Stata, R, or Python for quantitative analysis; ability to produce clear visualisations and accessible reporting.

- Availability to conduct field visits to Punjab and KP within the assignment period.

  - How to apply

Interested consultants or firms should submit the technical and financial proposal to two following emails atif.naveed@britishcouncil.org and Rizwan.mahmood@britishcouncil.org. For any queries, please contact Rizwan Mahmood (Senior MEL Lead) through email.

- Technical proposal: understanding of the assignment, proposed methodology, and workplan.

- Financial proposal: itemised budget with daily rates and estimated costs.

- CV of key personnel and at least two relevant evaluation samples.

  - Criteria for evaluation

Following Criteria would be used for Evaluating the proposals.

- Professional qualification relevant to the assignment (30%)

- Relevant experience of Education Programme Evaluations (20%)

- Technical Approach to carry out the assignment (20%)

- Responsiveness to GESSI in technical proposal (10%)

- Financial Proposal (Value for money) (20%)